...COLUMNWIDTH 45

Programmin� the

Performance Evaluation and Review �echnique (PERT)

in BASIC

"� method for plannin� complex activities

where no precedent� exist."

Origina� program by Steven Zimmerman and Leo M. Conrad

Developed and modifie� for the Osborne 1 by Doug Hurst

Tex� and program listin� reprinte�

from BYTE Magazine with permission.

#TABLE OF CONTENTS#

#Osborne 1 Prolog# . . . . . . . . . . .    2

#Introduction.#  . . . . . . . . . . . .    3

#Origins o� PERT.# . . . . . . . . . . .    3

#The Start o� PER� Analysis.#  . . . . .    3

#The Bubble Diagram.#  . . . . . . . . .    4

#The Critical Path.# . . . . . . . . . .    4

#Three Time Estimates.#  . . . . . . . .    5

#Our PERT Program.#  . . . . . . . . . .    5

#Runnin� the Program.# . . . . . . . . .    6

#Conclusion#.  . . . . . . . . . . . . .    8

#Figure 1#  . . . . . . . . . . . . .    9

#Tabl� 1# . . . . . . . . . . . . . .   10

#A Glance at the Mathematic� of PERT#   11

Programming PERT i� BASIC

"A method fo� planning complex activities

wher� no precedents exist."

Original program b� Steven Zimmerman and Le� M. Conrad

Developed an� modified for the Osborn� 1 b� Dou� Hurst

Text and program listing reprinted

from BYTE Magazin� wit� permission.

...T1

#Osborne � Prolog#

The BYTE article from which this librar� submission wa�

extracted appear� on pages 465-478 o� the May 1982 issue with the �

theme "Japanese Computers.

This was � fairly easy progra� to convert to run on th� O-1

as are most programs writte� in TRS-8� Level II or Disk

Basic(als� by MicroSoft)� Deletion� to the progra� include all

tape save and load routines. Additions include a means by which �

to designate time units used and project start dates as well as

their appearance on th� har� cop� output. Also, and most �

important, is the inclusion of th� ability to display and �

printout a GANNT Chart of th� pertinen� PER� elements.

Th� program has great practical utility.  At th� Marine

Corp� Communication-Electronics School, Twentynin� Palms, CA, we

ar� involved in a larg� number o� courseware conversions (to

Computer Aided Instruction(CAI)) that are spread out, in some

cases� ove� periods as large a� years. PERT has been instrumental

in both the planning and monitoring o� these projects.

There are now 3 main programs o� the diskette, PERTSAMP.COM, �

PERT80.BAS, and PERT128.BAS. PERTSAMP.COM i� somethin� I'm really

proud of, although I can'� tak� ful� credit for th� originality. �

I pulled a program called OSBOARD1.COM off Kelly Smith's CP/M Net

� while back. I� was really an advertisement for a program which �

makes th� O-1's graphic� eas� to use. In doing s� it showe� the

program's capability. PERTSAMP.COM does much th� same. Just place

the PERT diskette i� the A drive and hi� the return.

IMPORTANT ! Make sure you printe� is up when yo� do so.

What yo� wil� get is a complete sampl� run of the PERT program

including printouts. You should do this right away even though

PERT hasn't even been explained yet.  The � pages of output ar�

Listings 2,3,4,and 5 as referre� to in th� article proper.

PERTSAMP i� compiled BASIC. PERT80/128.BAS ar� named based o�

their printer requirements� TEM� is merel� a file which you may

read into the program for practice.

Wit� the latest addition, that is- the GANN� Chart, this

PERT program i� swiftly approachin� the quality o� MILESTON� (on

th� Osborne Approved Software list: Organi� Software� Retail

Pric� $295.00)�

(Note� My friend, fo� the time being, Jerry Lawson� has been

ploddin� awa� at PERT'� companio� program "Programming th�

Critical Path Method in BASIC", (BYTE, July 1982, pages 378-390)

for quite some time now. I forced him t� do it because so much

can be learned abou� programing from th� copying and debugging

process. It's been � slo� process and beside� he has a wife and �

family t� which he is more devote� tha� his Osborne. Can't

understand that. When he finishe� his part� the program will b�

cleane� up, modified and submitted. Once this is done, MILESTONE

will have been equaled.)

...T1

#Introduction.#

The Performance Evaluation and Revie� Techniqu� (PERT) i� a

powerful metho� of planning comple� activities, especially �

pioneering project� lik� the creation of a new business or the �

development o� a new machine� The innovativ� nature o� these

projects assure� tha� few precedent� exist to help estimate �

performance time.

PERT give� managers the tools to deal with uncertainty� PER�

i� management in action.  It plans, schedules, and controls

activity. Usin� PERT, contractors, builders, engineers� and

businessmen can improv� planning in the midst o� uncertainty and

save money as a result.

Until now, only larg� businesses with access to large

computers coul� use PERT� The program i� listing � (Listing 1 ma�

b� obtained by loadin� either PERT80.BAS or PERT128.BAS, setting

WIDT� LPRINT 80, an� the� doing a LLIST.) brings PERT'� power to

microcompute� users.

Before presenting our program� however, we'l� giv� you a

glimpse at PERT's history� briefly describe the nature of PERT

analysis, suggest on� possible PERT application fo� a manager,

and examin� the mathematics behind PERT.

...T1

#Origins of PERT.#

PERT date� bac� to � tea� created by th� Nav� Special �

Projects Office, Lockheed Aircraf� Corporation, and management �

consulting firm of Booz� Allen, and Hamilton. Work during World

Wa� I o� the Gann� scheduling chart and th� Gannt milestone chart

should also be note� because these precipitated the development �

of the networ� diagram (described later) used in PERT.

Manager� of many different kinds of tasks have successfully

applied PERT. One particularly spectacular result of th� PER�

approach is the Polaris missile� which also occasioned PERT's

development. (Lockheed Aircraft was the major contractor for

Polaris.) Completio� tim� was critical in th� Polaris program,

but there was considerable uncertainty about how long the

required activities woul� take.  Moreover, the start o� man�

activities depended o� the completio� of others. These are th�

chief reasons wh� PER� employs � network schem� and focuses o�

the probability of various activitie� finishin� at specified �

times.

...T1

#The Start of PERT Analysis.#

PERT analysis begins by reducing a project description to a �

lis� of event� and activities.  A� activity is a part of a

project that consumes resources or time an� has a definable

beginning and end. A� event is a point i� time, instant� The

beginning an� ending points of a� activity are events. To appl�

PERT t� a comple� project, you must identify all th� events

needed to complete the projec� and all the activities that resul�

i� the identifie� events.

As a� example, we'l� use a simplified versio� of an actual �

construction project that we just completed� To simplify, we'll

en� our example with the completion o� the building'� foundation.

We identified 18 activities needed to complete this foundation. �

Table 1 lists the activities� assigned letters A through Q and Z.

Each of th� nin� events i� the project consists of the completion

of one or more activities.

...T1

#The Bubbl� Diagram.#

Th� second stage in PERT analysi� is the layout of a

"bubble� diagram that shows how the necessary activities and

events form a sequence o� steps. Figure 1 is the bubbl� diagram �

of our foundation-building example. With or without PERT, �

specifying th� sequence of a project's step� is obviously an

important planning activity. Most contractors lay out the

sequence o� tasks in a project in some fashion, bu� PER� makes

task sequencing a formal activity. Formalizin� thi� process lends

valuabl� structur� to essential planning. In particular, makin� a

bubble diagram forces th� planner to specify whic� activities

depen� on the completion of others.

Diagrams like that shown in figure 1 ar� als� called

networks. A PERT network has one initia� event, a� the extreme

left� and one terminal event, at the extreme right. th� circles �

in figur� 1 (after you perform a littl� artwork) are numbered and

represent events. Th� lines ar� lettered and represent �

activities; each line has an arro� indicating it� directio� in �

tim� fro� beginnin� to completion� The network a� a whole shows

th� series o� activities that must be performed to complete th�

project. th� arrows show which activities and event� logicall�

preced� others.

An event that results from completion o� mor� tha� one

activit� is calle� a merge event� an event that represent� the

joint beginning o� mor� tha� one activity is called � burst

event� Before any activit� can start, al� precedin� activities

must be completed (but no� all simultaneously). An arrow's length

an� its compass direction are insignificant.

Dashed line� in network diagram� represen�

"dummy"activities. A dummy activity exist� whe� the completio� of �

one even� depends on th� completion of another but require� no �

additional work or activity. PERT handles dummy activities like

an� others but assigns the activity zero time and zero costs.

...T1

#The Critical Path.#

The longest route from the beginning o� the network o� the

left to its end o� the righ� determines th� tim� required to

complete the project. this line is the critical path, which

determines the minimum time required to complet� a job. Although

the concep� of � critical path may sound complex, it is simple

once you'v� lai� a projec� out in a bubble diagram.

Critical-pat� analysis can revea� way� to shorten th�

critical path an� to control th� total length of a job. Because

of th� siz� of our computer, this progra� analyzes the critical

path but does not attemp� to shorten it.

...T1

#Three Time Estimates.#

Along each activit� lin� in figur� 1, you see three decima�

numbers. These number� represen� an optimistic� likely and

pessimisti� estimate of the time require� to complete the

activity. Each time the activity is not on th� critical path� a

manager's decision to authorize expenditures for overtime would �

be foolish an� wasteful� All activitie� not on the critica� pat�

have "slack time," th� difference between the earliest and latest �

expected finish. B� definition, only the activities o� the

critica� pat� hav� zer� slack time. We'll elaborate later.

...T1

#Ou� PER� Program.#

Ou� PER� Program is shown i� listing 1. A dimension (DIM)

statement at line 160 provides places to store data on

activities� The same DIM statement also provides storag� for a

dummy variable,SV, t� be used later during sorts.

On a system with 32� (remembe� the article was written for �

TRS-80� bytes of memory an� two disk drives, our program can �

handle more than 200 activities. We have ye� to need more than �

100 activities. Your machine's memory capacity and th� limits o�

your DIM statement will determine th� siz� of the proble� tha�

our program can handl� for you. You can find the limits by

experimentation.

On� way to save memory is t� carefull� omi� remark (REM) �

statements(These statements are left i� in fn.ft PERTSAMP.BAS but

have been removed from PERT80.BAS and PERT128.BAS in th� Osborne �

1 version).

As noted before, th� critical path consists of a serie� of �

activities that have zero slack time. To find th� critical path�

you must identif� activities that have zero slack time. The

program output� consisting of two tables, is designed to identif�

these activities.

Th� first table (see listin� 2) shows the program's input�

listin� all the activities in the project� their beginning an�

ending events, and th� three estimates of the time each activity

requires. You shoul� check your input whenever yo� use this

program because otherwise you ma� get craz� results.

The second table (see listin� 3) is th� program'� output. �

Notice the last column, "Slack Time." Zeros in this column

identif� the critical path. You can, of course, trac� the

activities i� the critical path by looking in the first column�

"Code,� for each activity with zero slack time� But our program

also provides a menu option CRITICA� PAT� AND TIME� which permits

both th� critical path and the time required to complete it.

Familiarity with th� project and the program will probably �

mak� listings 2 an� 3 all yo� wil� nee� to fully monitor you

program.  Unfortunately, many times ther� wil� be � nee� to make �

the schedulin� of your project understandable to supervisors or

others without detaile� explanation. This is where listin� 4

becomes invaluable. Listing 4 is a GANN� chart fo� the project. �

Thi� chart ca� be heade� in eithe� one of two ways depending on

th� tim� estimate� in your DATA statements� Thi� wil� be eithe�

WEEKS or MONTHS. The GANNT char� header i� triggere� by you input �

on line 150. If yo� enter WEEKS your header will show 15 months

of 4 weeks each o� PERT80 and 2 years of weeks on PERT128� If you

pick MONTHS, you ge� 5 years of months on either PERT8� or �

PERT128. The GANNT Char� lists each activit� similar to listing�

2 and � and actually merel� provides a graphic representation of

listing 3�  Th� E represents the early start time� The @ and/or �

symbol represent the expected time for th� activity (C's if the

activity i� on the Critical Path). The L is for th� las� finish. �

By  default, any space between th� las� @ for an activity and the

� represents slack time i� the activity is started at the early

star� and is finished in the expected time. There will be n�

space between th� las� C and th� L for an� activity� As stated,

these lie on th� critical path and there is n� slack time.

A word of caution about using the program: round-off

problems in calculation the critical path forced us to define

zero slack time as 0.001 instead of true zero� Where small

differences ar� important, this approximatio� of zero can cause �

problems� The valu� 0.001 is entered i� lin� 1490; perhaps you �

can change th� value to true zero for some of your applications�

Furthermore� since we used statistical methods to determine the

probabilit� of � project'� being completed on time� given a �

schedule� completion date, you should remember that data

generated by the program is based on estimates an� is itsel� an �

estimate.

...T1

#Running the Program.#

The easiest wa� to input data is t� use DATA statement� at �

the end of th� program starting always at line number 4000�

Entering data from th� keyboard take� tim� and increases the �

number o� errors.  The best way d� the DATA statement� is to boot

up WordSta� in drive A an� the PERT diskette in drive B� Create a

file on driv� B i� the "N" non-document mode that pretty well �

discribe� you� project. Like "BUILDING.BAS"� Simply start using

line 4000 with th� number o� activities an� the number of events.

Then add each activity letter� description,starting an� ending

even� and lastly th� optimistic, likely� and pessimestic times, �

as below:

4000 DATA 18,9

4010 DATA A,ACCT. PAPERS,1,2,1,2,3

402� DAT� B,SHOP BANKERS,1,3,2,4,6

4030 DATA C,SHOP REAL EST.,1,4,1,13,17

ETC......

Once this is done, save the program. No� boo� up MBASI� and LOAD

"x:PERT80" o� "x:PERT128". MERGE "x:BUILDING" t� append your DATA

line� to the progra� the� SAV� "x:BUILDING" (x: = the disk drive

of choice). This saves the entir� program under the name formerly

used by your DATA lines and leaves PERT80/12� intact withou� dat�

lines and available for future projects. The following �description of a program run assumes that DATA statements were

used for input.

Whether you input data from DATA statement� or the keyboard,

the program begins by giving the identification messag� and then

displays:

*** NOTE BEGINNING EVENTS

WILL B� SORTED INTO

NUMERICAL ORDER ***

when asking

DIMENSIONS FOR ACTIVITIES?_

(NOTE: This will only appear if data is t� be entered from

keyboard or disk file.)

TIM� UNITS WILL BE MEASURED IN?_

and

PROJECT START DATE?_

As yo� see in listin� 2, event� are arranged according to

the earliest startin� event in each activity, and ties are broken

by reference to the earlies� ending event for each activity.

Now the program presents the input menu:

INPU� MENU

K KEYBOARD

D DISK FILE

Option R causes th� program to read DATA statements a� the

en� of the program. After a brie� delay, the program will display

for verification th� input of what was read.

The vide� display of th� input will look slightl� differen�

than the table i� listing � because of th� differences i� the

screen and printe� sizes. I� a single screen won't accommodate

al� the input, th� program will ask you to page through.

Afte� listing all the input, the progra� wil� say:

-2 ADD, -1 TO CONTINUE OR NUMBER TO CHANGE?_

Th� number referred to is the number of an� activity that you �

wis� to change.  Assuming yo� wan� to continue and enter -1, th�

progra� wil� ask:

HAR� COP� OF INPUT DATA (Y/N)?_

If you reques� har� copy, th� program will print 3 lines o� EGO

data an� the� asks:

TITLE?_

DATE?_

and will print your responses� as well as th� measure of time

units at the to� of the page. Our sample set of data used th�

title PERT SAMPL� and the date 11/26/82.�     Afte� the inpu� is printed, the screen will display th�

results, as show� in listing 3. For each activity, you will see

computations of how long it should be expecte� to take, the �

earliest week (you may use months also� it can start, the �

earliest it can finish, and the slack time (the difference

between the earliest and latest possible finish). Yo� may have to

page through a screen display of this data. The progra� wil�

again ask i� you want hard copy.

Next th� GANNT Chart will b� displaye� wit� paging again if

necessary and a prompt fo� har� copy. Lines 8� and 90 set screen �

and printer width to accomodate all requirements.

Then you will see:

OUTPU� MENU

C CRITICA� PAT� AND TIME

D DISK

E END

� RECYCLE

SELECTION?_

Option C, for ou� example, results i� a displa� lik� the

following:

CRITICAL PATH

C I K � P

TIM� OF CRITICAL PATH

42.33

SCHEDULE� PROJECT TIME (USE SAME TIME UNITS AS DATA)?_

For our example� the critical path consists o� shopping for �

a real-estate agent, obtaining land, gettin� architectural plans,

getting a detailed layout for construction, and actuall� building

th� foundation. The time of the critical path i� expected to b�

42.33 weeks�

You ca� now inpu� the scheduled time for the project, an�

the program will use the Z calculations explained i� the textbox

"A Glance at the Mathematics of PERT" t� tel� you a probability �

of meeting th� schedule� As shown in listin� 3, there is a

0.0123852 probability of finishing in 35 weeks and a 0.990536 �

probability o� finishin� in 50 weeks. As noted earlier, there i�

also a .500 probability of finishing in the expecte� tim� of the

critical path - 42.33 weeks.

...T1

#Conclusion#.

If yo� nee� hel� planning and scheduling complex projects,

this PERT program can provide it. You can us� it without knowing

ho� to perform th� calculations involved. Although w� repeat our

caution about relyin� on estimate-based estimates, we still �

believe PERT has proved itself a valuable managerial tool and

that our program accurately represents PERT.

�                                  _

|#2#|                                |#7#|

_

|#8#|

_

_                _                  _                      |#9#|

|#1#|              |#3#|                |#5#|

_                     _

|#4#|                   |#6#|

(NOTE: Since it is impossibl� to draw � ful� fledged bubbl� diagram with �

WordStar� perform the following upon printing this documentation. Connect the �

bubbles and label the resultant lines as shown below.

1-2  A-1,2,3             4-5  I-8,11,13

1-3  B-2,4,6             5-6  J-2,3,4

1-�  C-2,13,17           5-�  K-2,5,12

2-3  D-2,4,5             5-8  L-1,2,4

2-�  G-1.4,2.2,6.�       6-�  M-2,3,4

2-6  F-.4,1.3,1.5        6-9  O-1,2,5

2-7  Z-4,5,8             7-8  N-9,11,12

3-4  E-3,4,5             7-9  Q-1,2,3

3-�  H-2,4,6             8-�  P-1,3,6

...T2

#Figure 1#

The PERT network diagram o� the activitie� required to build � foundation.

Each circle represents a� event an� eac� lin� between circles represents one of

th� activities listed in table 1� The thre� numbers given for each activity

represent huma� estimate� of the optimistic(minimum), likely, an�

pessimistic(maximum) time in weeks that each activity will take. The network has �

one initial event, even� 1 a� the extreme left and on� terminal event, event 9

at the extreme right. The critical path is the one that takes the most time t�

get from event 1 to event 9.

Letter    Activit�                   Beginning     End

Event      Event

�       assembl� accounting data      1           2

�       look fo� ban�                 1           3

�       look fo� real-estate agent    1           4

�       seek permits                  2           7

�       make market study of area     2           3

�       look fo� contractor           2           5

�       seek insurance fo� con-       2           6

struction

H       get basic architectural plans 3           5

E       make cost study               3           4

I       buy land                      4           5

J       list materials                5           6

K       get more detaile� architec-   5           7

tural plans

L       hav� survey made              5           8

M       buy firs� batch of materials  6           8

O       buy second batch o�           6           9

materials

�       complet� detailed internal    7           8

layout of foundation

Q       hire crew                     �           9

P       build foundatio�              �           9

...T2

#Table 1#

The activities required t� build a foundation� the program i� listing � use� the

letters at left t� identify the activities� The two columns at righ� lis� the

first and last event during each activity. An event is th� completion of one or

more activities.

...T2

#A Glance at the Mathematics of PERT#

The mathematics of PERT involves some interestin�

statistical concepts. You don't have to understand the

mathematics to use PERT, but it helps you to understan� how our �

program works.

First, we must refresh your recollection o� som� basic

statistica� terms. the mean of a se� of occurences of some

variable is th� arithmetic average of the values of th�

occurences; the standard deviation i� the square root of the mean �

of the square� of the deviations of individual occurences from �

the mean); th� variance is the square of th� standard deviation.

Fo� example, if w� hav� three values 9.12 and 15, their mean

is 36/3=12, their variance is

(9-12)� + (12-12)2 + (15-12)2 = 18

and the standard deviation i� the square root of 18, which is

approximately 4.24.

It is a commo� statistical assumption that the standard

deviation in unimoda� distributions (distributions that have only

a singl� most-likely occurring value) is roughl� a sixth of th�

range of distribution lies with thre� standard deviation� of the

mean� and for the normal distribution, 99.7 percent of the �

distribution lies withi� three standar� deviations of the mean.

Since we have estimates of the minimum time  a  and the

maximum time  b  required to complete an activity, we have

established an estimated rang� of actua� times. W� can estimate �

the standard deviation of th� actual time as

#(b-a)#

6

Sinc� PER� assumes that chance, or random factors will

influence th� actual time needed to complete an activity, we can

expec� the actual times t� be distribute� along some curve. PERT �

assumes that the mean actual time will follow th� distribution �

known as the beta distribution, which is contained in a finite �

interval and may b� either symmetric o� skewed. Our most likely

time of completio�  m  is the mode of the curve for each �

activity� the following equation, base� on the assumption that �

our formula for th� standard deviation is correct, is linear

approximation o� the valu� of the expected value, EV, o� the mean

time:

(a+4xm+b)

EV = ----------

6

A� you can see, this is just a weighted average, countin� the

minimum and maximum each once an� the mode four times, then

dividing the total b� 6. On line 99� of listing 1, same equation �

is expressed as:

A(I,6)=(A(I,3)+4*A(I,4)+A(I,5)/6

The following equatio� gives th� variance of the beta

distribution fo� eac� activity:

VAR =((b-a)/6)2

For each activity, th� program applies th� statistical

principle� describe� above an� calculates th� tim� the activity �

should last, the earliest time at whic� it can start, the �

earliest finish, the latest start� and the lates� finish. �

Calculation o� the earliest start and finis� times is called th�

"forward pass" and takes place in ou� program at lines 970 to

1080. Calculation of the latest start and finis� is calle� the

"backward pass" and takes place at lines 1090 t� 1230.

The difference betwee� the earliest and latest projected

finish for each activity is called "slack time"� At lines 1240 to

1290� the program calculates slack time for each activity. The

even� tha� hav� zer� slack time form th� critical path.

To obtain th� approximate variance fo� the critical path,

ad� the variances of the activities o� the path:

VAR(Path)=VAR(1)+VAR(2) ....+VAR(n)

I� happens that the Centra� Limit theorem enables us, based o�

the foregoing, t� assume that the distribution of the time

required t� complete the critical path i� normal. Based on this

assumption, we can calculate the probability of the project's

being on time, given some specified target completion time. The

calculation's basis is the deviation of the scheduled completion

time from th� estimate� mea� completion with th� deviatio�

measured in unit� of standard deviations. This deviation is

called Z. The � calculation for th� standard normal table is:

(scheduled             time of  )

�   time           critical path)

Z � ----------------------------------

VAR(Path)

Rather than require you to use norma� tables with our

program, w� hav� built in a Taylor serie� to approximat� the

tables. (A Taylor series is a power series that give� the

expansion of a functio�  f(x)  i� the neighborhood o� a point a,

provided all derivatives exist and � series converges.) The �

Taylor series is locate� at line 2440 and following i� our

program.

Th� expected time of the critica� pat� is the sum of the �

expected time� of all the activities o� the path� If the

scheduled time of the project equals th� expected time of the

critical path, you have a 50 percen� chance o� completing th�

projec� on time.

#########################################################################################################################